## Slide 1: PMGDISHA
Implementation of PMGDISHA in Village Secretariats

## Slide 2
About PMGDISHA
Pradhan Mantri Gramin Digital Saksharta Abhiyan is the scheme to make 6 crore persons in rural areas, across States/UTs, digitally literate, reaching to around 40% of rural households by covering one member every eligible households
Eligibility Criteria for enrolment
  Age Group :14-60 years,
  IT illiterate,
  One person per household (Beneficiary identification through Aadhaar/eKYC). Preference would be given to SC, ST, BPL, Minorities, women, and differently abled persons
Examination
  The examination should be conducted in the Secretariat and needs Fingerprint scanner device for invigilator authentication and Webcam for citizen to proceed for the test
  The duration for the examination is 1 hour
  Only one student can take an exam at a time per one computer

## Slide 3
Role of Secretariat Functionaries
Panchayat Secretary
  Ensure WEA and DA are performing the assigned tasks
  Ensure the target of 300 is achieved per Gram Panchayat
  May involve Volunteers for motivation
Welfare Education Assistant
  Motivate SHG women for enrollment with special focus on women with disability or women from SC/ST/OBC/Minority communities
  Ensure not more than 1 person per family is enrolled under the program
Digital Assistant
  Registration of interested candidates in PMG DISHA portal using Aadhaar biometric authentication
  Ensure the enrolled candidates go through all the resource material and complete the mandated training within 10 days from the date of registration
  After completion of training, conduct examination for candidates after 10 days from date of registration – Ensure assessment of every enrolled candidate is completed within 20 days from the date of registration

## Slide 4: Work flow of PMGDISHA
Creation of GSWS as Training partner
Approval of GSWS as training partner by CSC
Addition of Training Centres (Village Secretariats ) in the PMG Disha portal with Area details and Trainer details (DA)
Approval of Training Centre (Village Secretariat) in PMGDISHA portal by CSC
Same will be reflected in GSWS state dashboard
https://www.pmgdisha.in/
The Trainer (DA) will enrol the Citizen/SHG women in their login and initiate the training for 10 days
After the completion of training the citizen will appear for the test after 10 days from date of registration and must be completed within 20 days
After every successful certification of Citizen for Digital Literacy under PMGDISHA, GSWS Department shall receive an incentive
Orientation to Trainer (DA) for implementing PMGDISHA Program.
The session will be of 60 mins, to be given by CSC / GSWS Department using videos and user manual

## Slide 5
Activity | Responsible person | Instructions | Status
Registration of GVWV & VSWS Department as Training Partner | Department | - | Completed
Registration of Village Secretariats as Training Centers | Department | - | Registered 1000 Village Secretariats as Training Centers as on 4-May-22
Approval of Village Secretariat as Training Center | Digital Assistant (DA) / In-charge DA | Download location app shared on mobile and generate location code Log on to https://www.pmgdisha.in/app/login Username and password are shared on registered email ID Update the location code in the portal Verify email ID (guidelines already issued) | 155 Village Secretariats are approved as Training Centers as on 4-May-22
Training of DAs / In-charge DAs | Department | All approved 155 Village Secretariat must attend the training on 5-May-22 | Webinar link shared on email and WhatsApp
Instructions to be followed

## Slide 6
Action Plan
S. No | Activity | May |  |  |  | Jun | Jul | Aug | Sep | Oct | Nov | Dec
 |  | W1 | W2 | W3 | W4 |  |  |  |  |  |  | 
1 | Registration of Training Centers |  |  |  |  |  |  |  |  |  |  | 
2 | Orientation training to DAs on PMGDISHA |  |  |  |  |  |  |  |  |  |  | 
3 | Motivating candidates for enrolment |  |  |  |  |  |  |  |  |  |  | 
4 | Registration of Candidates |  |  |  |  |  |  |  |  |  |  | 
5 | Training registered candidates |  |  |  |  |  |  |  |  |  |  | 
6 | Conducting assessment to registered candidates |  |  |  |  |  |  |  |  |  |  | 

## Slide 7
For every successful certification, GVWV & VSWS Department as a Training Partner shall receive Rs. 300, which shall be divided and shared with the stakeholders involved, in a proportion as decided by the Government
Proposed Incentive

## Slide 8: THANK YOU